# Scoping update — status through 6 October 2026

Research question (unchanged): does feedback on earlier cases improve later, independent cases? Spike-sorting F1 is the task metric, not the research result.

# Roadmap (changes in bold)

- Stage 1 (finishing) — feedback environment and reproducible baselines.

- Stage 2 — controlled feedback reuse. Conditions: no feedback / retrieve corrected cases / cases + expert explanation / feedback distilled into SKILL.md (proposed fourth arm, per meeting note 4).

- Stage 3 — rationale-level feedback. Logged rationale rows in the action sheet: CH3 97, CH31 54, CH30 90, CH20 45 (only the first 43 replayable). The 9/23 figure "248" does not match these counts; one count definition is needed.

- Stage 4 — scale and safe rollout. The 311-action "untouched" test block (e004_004-006 = CH3/CH31) is no longer untouched; test data must be redefined (see Question 3).

- Stage 5 — real-scientist feedback versus the simulated expert.

# Key results since 23 September

| Run | CH3 | CH20 | CH30 | CH31 | Mean |
| --- | --- | --- | --- | --- | --- |
| No-model control (keep initial clusters ≥5,000 spikes) | 0.257 | 0.365 | 0.310 | 0.521 | 0.363 |
| GPT-5.1 medium, pinned upstream code, seed 0 (9/28) | 0 | 0 | 0.710 | 0.723 | 0.358 |
| GPT-6 Astra high, upstream controller (9/29–30) | stopped* | not run | 0.334 | 0 | — |
| Historical GPT-5.1 artifact (not reproducible) | 0.751 | 0.895 | 0.716 | 0.725 | 0.772 |

*CH3 stopped at call 85 (API error); Astra CH3/20 used a different (protected) controller. Astra cost ≈ $43 at standard rates.

- Controlled reproduction is done: two medium-effort reruns (9/23: 0.359; 9/28: 0.358). The "reasoning_effort = null" hypothesis is ruled out; the historical 0.77 is not reproducible.

- Under the old harness, the agent ≈ doing nothing (0.358 vs 0.363). Comparing models under it is not meaningful.

- Decisions are not discriminative: Astra discards expert-pure clusters 36% of the time (20/55) vs pure-noise clusters 34% (121/358).

- More decisions → more loss: Phase-1 decisions on CH30: GPT-5.1 28, Astra 290; expert unit 31 judged 2 vs 28 times. Astra keeps splitting pure expert units, then discards the fragments on morphology; on CH30 it also retained ~95k noise spikes.

- First divergence happens on byte-identical input (CH30 call 6, CH31 call 1): same prompt, images and state, different action, so it is not a harness bug.

- Old prompt rules (written for weaker-vision models) drive the failures:

  - "many subclusters → split" is always true for large pure units (84% of Astra SPLIT rationales cite the tree);

  - "single smooth return to baseline" rejects normal triphasic spikes, partly because the 1.5 ms window truncates recovery (96% of DISCARD rationales cite tail/rebound);

  - the ISI threshold 0.006 has no unit.

# Corrections to the 23 September document

- §5 "VLM + rules baseline": correct values are P/R/F1 = 0.2327 / 1.0000 / 0.3712 (0.3634 was a mixed-up row). That historical run actually called gpt-4o (run log), despite being labelled gpt-5.1.

- §5 "controlled reproduction not yet performed" → done (see above).

- Task 5 (re-establish autonomous baseline) → done (GPT-5.1 + Astra, full manifests).

# Current work: frozen-skill closed-model baseline (before Stage 2)

- Offline, done: prompt split into a fixed system contract + skill (system_v1; skill_v0 = old rules verbatim; skill_v1 = revised candidate); 35 development replay cases (16 expert-logged, 19 terminal-constraint), reusing saved images.

- Controller v1: no 500/5,000 size filters (the 5,000 filter deletes 2 of 9 expert units); NOT_MERGE preserves the cluster; 4-view Phase 1.

- In progress: replay runner + pre-registered scoring for v0 vs v1. No paid call yet.

- Then: one dev-channel rollout → freeze harness v1 → closed-model zero-shot baseline → Stage 2.

- Held-out: e007_012-017 reserved from now on (it was used earlier for RF training, so it is not pristine). There is currently no clean held-out block.

# Weekly tasks (23–29 September) — status

| # | Task | Status |
| --- | --- | --- |
| 1 | Simulated-expert labels, 16 datasets (Zixuan) | to confirm |
| 2 | CH30 table with 2-class F1 + trivial rows (Tengyang) | done (in 9/23 doc) |
| 3 | Action-space patch: NOT_MERGE log, large–large merge, merge/undo (Zixuan) | to confirm |
| 4 | Qwen3.5-9B LoRA (Tengyang) | deferred until after the closed-model baseline |
| 5 | Re-establish autonomous baseline | done |
| 6 | Stage 2 design note | to confirm |

# Meeting notes — follow-up

- Note 2 (best model once, analyse failures): done. Rationale keyword analysis done; a full rationale summary is still to do.

- Note 4 (SKILL.md co-adaptation): system/skill split done; switch the skill format to SKILL.md.

- Notes 3, 7, 8 (OpenRouter online; QA with Chuanyang Jin; compute from Yifan): pending.

# Questions for the advisor

- Budget for skill validation: replay ≈ 70–210 calls (~$3–10), plus one dev-channel rollout (~$10–30).

- Should SKILL.md updates be human-reviewed from the start (a cheap first form of human-in-the-loop)?

- Stage 4 test data: with no untouched block left, should we use a reserved block (with prior exposure disclosed) or wait for new recordings?

- Should continual learning start from the tuned expert skill or from a minimal skill (the original Harness B)? Fixed workflow or tool-style agent?

- One labelling rule for both workstreams: should the simulated-expert oracle (§9) also be the scoring reference for the skill replay?